KEY DATES AND DEADLINES

| STAND PLANS, ORDERS and CONTRACTORS Registration |  |  |
| --- | --- | --- |
| 05 October 2016 |  | Deadline for Venue exclusive services with advance rates. |
| 14 October 2016 |  | Deadline for main contractor’s non-exclusive services order forms with advance rates. |
| 14 October 2016 |  | Deadline for submission of Stand Plans for all stands. |
| 28 October 2016 |  | Deadline for submission of the Deposit Against Damages Form. |
| 28 October 2016 |  | Deadline for application of the Contractor pass form. |
| 28 October 2016 |  | Final review of Stand Plans must be completed by this date at the latest. |
| 7 November 2016 |  | Deadline for all services order forms with standard rates. Onsite rates apply after this date and upon availability. |
| ASSEMBLY |  |  |
| 8 November 2016 | 07:00 to 13:00 | Preparation of the exhibition infrastructure by the main contractor and Venue management. |
| 8 November 2016 | 13:01 to 24:00 | Assembly of stand construction/set-up work starts. N.B. Contractors with large stands wishing to start earlier may contact the main contractor and Venue Management to discuss options with cost implications. |
| 9 - 11 November 2016 | 07:00 to 24:00 | Construction/set-up continues. |
| 12 November 2016 | 08:00 to 24:00 | Turnkey stands hand-over for clients to install equipment. |
| 13 November 2016 | 07:00 to 18:00 | Final day for set-up / rehearsal / decoration and equipment testing. All stand construction must be completed with exhibits in place and aisles cleared of any packing material and/or equipment. |
| 13 November 2016 | 18:00 22:00 | Final cleaning. Exhibition closed for security protocol measures. |
| 14 November 2016 | 08:00 09:30 10:30 12:00 18:00 19:00 | Venue is under Security Restricted Access with x-ray & metal detectors in position. Access to halls for exhibitor working staff. Opening Ceremony (OC) in Royal Jubilee Ballroom. VIP tour of the exhibition immediately after OC. Exhibition open to all. Exhibition closed to delegates and visitors. Exhibition closed to all exhibitor working staff. |
| 15-16 November 2016 | 08:00 10:00 18:00 19:00 | Access to halls for exhibitor working staff. Exhibition open to all delegates and visitors. Exhibition closed to all delegates and visitors. Exhibition closed to all exhibitor working staff. |
| 17 November 2016 | 08:00 10:00 16:00 | Access to halls for exhibitor working staff. Exhibition open to all delegates and visitors. Exhibition closed. All delegates and visitors should proceed to Farewell Reception. |
| DISMANTLING |  |  |
| 17 November 2016 | 16:01 to 19:00 19:01 to 24:00 | Carpet removal/return of empties. Move out of hand-carried goods only. No removal of any kind of stand construction materials. Detailed dismantling arrangements to be communicated later. |
| 18 November 2016 | 08:00 to 24:00 | Dismantling move out continues. |
| 19 November 2016 | 08:00 to 18:00 18:00 to 22:00 | Dismantling move out continues. All stands to be dismantled and cleared from the Exhibition Halls. Final cleaning. |

N.B.:  All the above dates and times are based on standard local Bangkok time.